## MSEL
2019 Statewide HurrEx UAS Component - Master Sequence of Events List (MSEL) - Particpant Advance Copy
Updated 3MAY19 / 0830
Event # | Inject Time | From | To | Responsible Controller | Inject Means | EEG | Key Event | Related Events
UAS1 | Day 0 / 1200 | n/a | n/a | All Controllers
Event Description | StartEx |  |  | Expected Action | Commence exercise
Originator | Controllers
Controller Notes | n/a
Implementer | Exercise play begins in all locations.
Event # | Inject Time | From | To | Responsible Controller | Inject Means | EEG | Key Event | Related Events
UAS2 | Day 0 / 1200 | n/a | n/a | All Controllers | Verbal | No | Yes
Event Description | Exercise Briefing, Day 1 |  |  | Expected Action
Originator
Controller Notes
Implementer
Event # | Inject Time | From | To | Responsible Controller | Inject Means | EEG | Key Event | Related Events
UAS3 | Day 0 / 1230 | County EOC/State EOC | UAS Operations | All Controllers | Email/Slack | n/a | Yes
Event Description | Situational Awareness/Recon - Streaming Request |  |  | Expected Action
Originator
Controller Notes
Implementer
Event # | Inject Time | From | To | Responsible Controller | Inject Means | EEG | Key Event | Related Events
UAS4 | Day 0 / 1230 | County EOC/State EOC | UAS Operations | All Controllers | Email/Slack | n/a | Yes
Event Description | Situational Awareness/Recon - Streaming Request - Miami |  |  | Expected Action
Originator
Controller Notes
Implementer
Event # | Inject Time | From | To | Responsible Controller | Inject Means | EEG | Key Event | Related Events
UAS5 | Day 0 / 1230 | County EOC/State EOC | UAS Operations | All Controllers | Email/Slack | n/a | No
Event Description | Situational Awareness/Recon - Recording Request |  |  | Expected Action
Originator
Controller Notes
Implementer
Event # | Inject Time | From | To | Responsible Controller | Inject Means | EEG | Key Event | Related Events
UAS6 | Day 0 / 1330 | County EOC/State EOC | UAS Operations | All Controllers | Email/Slack | n/a | Yes
Event Description | Damage Assessment Request |  |  | Expected Action
Originator
Controller Notes
Implementer
Event # | Inject Time | From | To | Responsible Controller | Inject Means | EEG | Key Event | Related Events
UAS7 | Day 0 / 1330 | County EOC/State EOC | UAS Operations | All Controllers | Email/Slack | n/a | No
Event Description | Damage Assessment Request, Levee or Waterway |  |  | Expected Action
Originator
Controller Notes
Implementer
Event # | Inject Time | From | To | Responsible Controller | Inject Means | EEG | Key Event | Related Events
UAS8 | Day 0 / 1330 | State EOC/FSU EM | UAS Operations | All Controllers | Email/Slack | n/a | Yes
Event Description | Mapping Request, FSU Campus |  |  | Expected Action
Originator
Controller Notes
Implementer
Event # | Inject Time | From | To | Responsible Controller | Inject Means | EEG | Key Event | Related Events
UAS9 | Day 0 / 1445 | State EOC | UAS Operations | All Controllers | Email/Slack | n/a | No
Event Description | Mapping Request, Division C |  |  | Expected Action
Originator
Controller Notes
Implementer
Event # | Inject Time | From | To | Responsible Controller | Inject Means | EEG | Key Event | Related Events
UAS10 | Day 0 / 1445 | County EOC/State EOC | UAS Operations | All Controllers | Email/Slack | n/a | No
Event Description | Damage Assessment Request |  |  | Expected Action
Originator
Controller Notes
Implementer
Event # | Inject Time | From | To | Responsible Controller | Inject Means | EEG | Key Event | Related Events
UAS11 | Day 0 / 1500 | County EOC/State EOC | UAS Operations | All Controllers | Email/Slack | n/a | Yes
Event Description | Situational Awareness/Recon - Streaming Request |  |  | Expected Action
Originator
Controller Notes
Implementer
Event # | Inject Time | From | To | Responsible Controller | Inject Means | EEG | Key Event | Related Events
UAS12 | Day 0 / 1530 | County EOC/State EOC | UAS Operations | All Controllers | Email/Slack | n/a | Yes
Event Description | Situational Awareness/Recon - Recording Request |  |  | Expected Action
Originator
Controller Notes
Implementer
Event # | Inject Time | From | To | Responsible Controller | Inject Means | EEG | Key Event | Related Events
UAS13 | Day 0 / 1600 | County EOC/State EOC | UAS Operations | All Controllers | Email/Slack | n/a | No
Event Description | Damage Assessment Request |  |  | Expected Action
Originator
Controller Notes
Implementer
Event # | Inject Time | From | To | Responsible Controller | Inject Means | EEG | Key Event | Related Events
UAS14 | Day 0 / 1600 | State EOC | UAS Operations | All Controllers | Email/Slack | n/a | No
Event Description | Mapping Request, Division A |  |  | Expected Action
Originator
Controller Notes
Implementer
Event # | Inject Time | From | To | Responsible Controller | Inject Means | EEG | Key Event | Related Events
UAS15 | Day 0 / 1700 |  |  | All Controllers | Email/Slack | n/a | No
Event Description | Evening stand down |  |  | Expected Action
Originator
Controller Notes
Implementer
Event # | Inject Time | From | To | Responsible Controller | Inject Means | EEG | Key Event | Related Events
UAS16 | Day 0 / 1900 | State EOC | UAS Operations | All Controllers | Email/Slack | n/a | Yes
Event Description | SAR Request |  |  | Expected Action
Originator
Controller Notes
Implementer
Event # | Inject Time | From | To | Responsible Controller | Inject Means | EEG | Key Event | Related Events
UAS17 | Day 0 / 2200 |  |  | All Controllers | Email/Slack
Event Description | End Day 0 |  |  | Expected Action
Originator
Controller Notes
Implementer
Event # | Inject Time | From | To | Responsible Controller | Inject Means | EEG | Key Event | Related Events
UAS18 | Day 1 / 0900 | n/a | n/a | All Controllers | Verbal | No | Yes
Event Description | Exercise Briefing, Day 2 |  |  | Expected Action
Originator
Controller Notes
Implementer
Event # | Inject Time | From | To | Responsible Controller | Inject Means | EEG | Key Event | Related Events
UAS19 | Day 1 / 0930 | County EOC/State EOC | UAS Ops | All Controllers | Verbal | No | Yes
Event Description | Recon/SAR Request |  |  | Expected Action
Originator
Controller Notes
Implementer
Event # | Inject Time | From | To | Responsible Controller | Inject Means | EEG | Key Event | Related Events
UAS20 | Day 1 / 1015 | County EOC/State EOC | UAS Operations | All Controllers | Email/Slack | n/a | Yes
Event Description | Situational Awareness/Recon - Streaming Request |  |  | Expected Action
Originator
Controller Notes
Implementer
Event # | Inject Time | From | To | Responsible Controller | Inject Means | EEG | Key Event | Related Events
UAS21 | Day 1 / 1030 | County EOC/State EOC | UAS Operations | All Controllers | Email/Slack | n/a | No
Event Description | Damage Assessment Request |  |  | Expected Action
Originator
Controller Notes
Implementer
Event # | Inject Time | From | To | Responsible Controller | Inject Means | EEG | Key Event | Related Events
UAS22 | Day 1 / 1200 | County EOC/State EOC | UAS Operations | All Controllers | Email/Slack | n/a | No
Event Description | Damage Assessment Request |  |  | Expected Action
Originator
Controller Notes
Implementer
Event # | Inject Time | From | To | Responsible Controller | Inject Means | EEG | Key Event | Related Events
UAS23 | Day 1 / 1230 | County EOC/State EOC | UAS Operations | All Controllers | Email/Slack | n/a | Yes
Event Description | Situational Awareness/Recon - Recording Request |  |  | Expected Action
Originator
Controller Notes
Implementer
Event # | Inject Time | From | To | Responsible Controller | Inject Means | EEG | Key Event | Related Events
UAS24 | Day 1 / 1400 |  |  | All Controllers |  |  | Yes
Event Description | End Ex |  |  | Expected Action | End Exercise
Originator | Controllers
Controller Notes
Implementer
Event # | Inject Time | From | To | Responsible Controller | Inject Means | EEG | Key Event | Related Events
UAS25 | Day 1 / 1400 |  |  | All Controllers |  |  | Yes
Event Description | Participant Hotwash |  |  | Expected Action | Hotwash
Originator | Controllers
Controller Notes
Implementer
Event # | Inject Time | From | To | Responsible Controller | Inject Means | EEG | Key Event | Related Events
UAS26 | Day 1 / 1430 |  |  | All Controllers |  |  | Yes
Event Description | Particpants released |  |  | Expected Action | All particpants and controllers released
Originator | Controllers
Controller Notes
Implementer